PowerEnJoy

Politecnico di Milano

Industrial and Information Engineering Computer Science and Engineering

Cattaneo Davide

El Hariry Matteo

Frontino Francesco

## Project Plan Document

Contents

1. ***Introduction***
   1. Purpose and scope 3
   2. Definitions, acronyms and abbreviations 3
   3. Reference documents 4
2. ***Project size, cost and effort estimation***
   1. Overview 5
   2. Size estimation: function points 5
      1. Internal logic files 7
      2. External logic files 8
      3. External inputs 9
      4. External inquiries 12
      5. External outputs 13
      6. Overall estimation 14
   3. Costs and effort estimation: COCOMO II 15
      1. Scale drivers 15
      2. Cost drivers 17
3. ***Schedule***
4. ***Resource allocation***
5. ***Risk management***
6. ***Revision***
   1. Team work
7. ***Introduction***
   1. ***Purpose and scope***

Purpose of this document is to give details about how the project is managed during its development cycle. Function points and COCOMO costs estimation methodologies are taken into account to generate the tables reported in chapter 2.

* 1. ***Definitions, acronyms and abbreviations***

Here is a brief description of the most important actors and words used in our system:

* FP: Function Points
* ILF: Internal logic ﬁle
* ELF: External logic ﬁle
* EI: External Input
* EO: External Output.
* EQ: External Inquiries
* DBMS: Database Management System.
* API: Application Programming Interface
  1. ***Reference documents***

Specification Document:

\* Assignments 1 and 2 (RASD and DD).pdf

\* ITPD.pdf

Examples documents:  
\* Project plan example document.pdf

1. ***Integration strategy***
   1. ***Overview***

This section is specifically focused on providing some estimations of the expected size, cost and required effort of PowerEnjoy.

For the size estimation part we will essentially use the Function Points approach, taking into account all the main functionalities of PowerEnjoy and estimating the correspondent amount of lines of code to be written in Java. This estimation will only take into account the parts of the project that concur to the implementation of the business logic and will disregardthe aspects concerning the user interface.

For the cost and effort estimation we will instead rely on the COCOMO approach, using as initial guidance the amount of lines of code computed with the FP approach.

* 1. ***Size estimation: function points***

A function point is a "unit of measurement" to express the amount of business functionality an information system (as a product) provides to a user. Function points are used to compute a functional size measurement (FSM) of software.

An important assumption is that the dimension of PowerEnJoy platform is characterized based on the functionalities that it has to offer.

The Function Points approach provides an estimation of the size of a project taking as inputs the amount of functionalities to be developed and their complexity.

The estimation is based on the usage of figures obtained through statistical analysis of real projects, which have been properly normalized and condensed in the following tables:

For Internal Logic Files and External Logic Files:

|  |  |  |  |
| --- | --- | --- | --- |
|  | *Data Elements* | | |
| *Record Elements* | *1-19* | *20-50* | *51+* |
| 1 | Low | Low | Avg |
| 2-5 | Low | Avg | High |
| 6+ | Avg | High | High |

For External Output and External Inquiry:

|  |  |  |  |
| --- | --- | --- | --- |
|  | Data Elements | | |
| *File Types* | *1-5* | *6-19* | *20+* |
| 0-1 | Low | Low | Avg |
| 2-3 | Low | Avg | High |
| 4+ | Avg | High | High |

For External Input:

|  |  |  |  |
| --- | --- | --- | --- |
|  | Data Elements | | |
| *File Types* | *1-4* | *5-15* | *16+* |
| 0-1 | Low | Low | Avg |
| 2-3 | Low | Avg | High |
| 4+ | Avg | High | High |

UFP Complexity Weights:

|  |  |  |  |
| --- | --- | --- | --- |
|  | Complexity Weight | | |
| *Function Type* | *Low* | *Average* | *High* |
| Internal Logic Files | 7 | 10 | 15 |
| External Logic Files | 5 | 7 | 10 |
| External Inputs | 3 | 4 | 6 |
| External Outputs | 4 | 5 | 7 |
| External Inquiries | 3 | 4 | 6 |
|  |  |  |  |

* + 1. ***Internal logic files (ILFs)***

This paragraph is going to show what kind of information PowerEnJoy has to store in its internal system in order to offer all the functionalities that will be furthermore explained.

Here is the list of ILFs the system must organize:

• Login data: the login details of the system are saved in two different cases of users indicated by a flag: System users and staff. For staff is an additional flag that differentiates the administrators by the operators. In this table in addition to the flags are posted username and password to enter.

• User data: user data is SSN, name, surname, date of birth, credit card number with security code, license number.

• Car info and status: The data being stored for each electric car are: an id (which is assigned by the system whenever a new vehicle is added to the system) and the license plate. Each car has a status which contains information concerning battery level, position (given by geographical coordinates of latitude and longitude).

• Ride and Reservations: For each ride are saved hours of booking the car start and stops (if it consists of more flights for each start and end time and costsaving intermediate), a progressive positions list, saved as route that trace the path of travel, the user who made the race.

Access permission info: to keep track of who has access to the administration system services, the staff account information is stored in a table. The main fields are first name, last name, user name, password and id of the privilege level of the account, which is related to the flag indicating if the account belongs to an administrator or an operator, which refers to a corresponding entry in a table privileges.

• API permissions: Finally, the system maintains a list of applications and plugins identifiers which have privileged access to the API. Each identifier is associated with the administrator contact information, a description of what the application or plugin and a list of methods that can be called.

Using the previously defined tables, this is the ILF functions points table obtained:

|  |  |  |
| --- | --- | --- |
| ILF | Complexity | FPs |
| Login data | Low | 7 |
| User data | Low | 7 |
| Car info | Low | 7 |
| Car status | Low | 7 |
| Queues | Average | 10 |
| Ride and Reservations | Low | 7 |
| API permissions | Average | 10 |
| Total |  | 55 |

* + 1. ***External logic files (ELFs)***

PowerEnJoy relies, for the collection of external information, on the Maps Service and on the Payment Gateway.

Regarding the Payment Gateway, the only interaction is given by the request for execution of a payment and the reception of the transaction outcome.

Concerning the Map Service, interactions are given by:

* request for location of coordinates of a provided address
* request of possible routes and estimated travel time from one location to another
* provide availability of a geographic representation of the area around a given position.

This is the information that maps must manage to provide the service used by user app, by the central system and by the staff browser.

The interaction between the core system and the remote service provider happens through a RESTful API and data can be returned in JSON or XML format. The results have then to be processed before they can be used as part of system’s computation.

Given the complexity of the interaction and the amount of data that is retrieved during the maps request and responses interaction, it is reasonable to classify the Maps Service logic file as complex. The Payment Gateway files though, are considered as simple ones, because of the trivial information exchange.

|  |  |  |
| --- | --- | --- |
| ELF | Complexity | FPs |
| ETA computation | Low | 10 |
| Reverse geocoding | Low | 10 |
| Map data retrieval  Request to Payment Gateway  Payment Gateway response | Low  Low  Low | 10 |
| Total |  | 30 |

* + 1. ***External inputs (EIs)***

External inputs that powerenjoy system receives different, given the multiplicity and include different possibilities of origin.

The inputs can come from web user interfaces, user apps, staff browsers and vehicle’s Board Controller.

Users App and staff Browsers:

• Login/Logout: these are simple operations that involve only the account manager. They contribute 3 FPs each.

User App and User Web Interface:

• Register a new account: this operation also has an average complexity, as it involves a number of checks on the validity of the fields. As such, it contributes 4 FPs.

User App:

• Password retrieval: this operation has an average complexity, as it involves a number of steps in order to be sure the user is really entitled to retrieve his password. For this reason, it contributes 4 FPs.

• Change settings: this operation also has an average complexity, as the number of settings to be managed can be quite high. As such, it contributes 4 FPs.

• Reserve a car: these are both very complex operations that involve a large number of components. For this reason they account for 6 FPs each.

• View profile information: since this is straightforward operation, it yields 3 FPs.

Staff browser:

Administrator side:

• Insert, delete and update Safe Areas: these are very complex operations that involve a great number of components. For this reason they account for 6 FPs each.

• Insert, delete and update Car and Car’s status: as for the zones, the complexity of these operations is high, so they account for another 6 FPs each.

• Request service statistics: as this operation involves some fairly complicated aggregate queries on the database, it can be considered complex and thus contributes 6FPs to the total amount.

• Grant and revoke privileges to an application or plugin: while these two specular operations involve a large number of fields that can be set, the impact on the database is quite limited. For this reason we think they have an average complexity and they should contribute 4 FPs each.

• Assign task to Operator:

Operator side:

• Search Car location:

• Send/receive messages:

• Create report:

• Update Car Status:

Board Controller:

• Send status info:

• Send Ride information:

*The final results are shown in the following table:*

|  |  |  |
| --- | --- | --- |
| EI | Complexity | FPs |
| Login/Logout | Low | 2x3 |
| Password retrieval | Average | 4 |
| Change settings | Average | 4 |
| Reserve a car | High | 2x4 |
| View profile info | Low | 3 |
| Register a new account | Average | 4 |
| View reservation history | Low | 3 |
| Insert, delete and update safe areas | High | 3x6 |
| Insert, delete and update cars/car status | High | 3x6 |
| Request service statistics | High | 6 |
| Grant and revoke app privileges | Average | 2x4 |
| Grant and revoke plugin privileges | Average | 2x4 |
| Search Car location Send/receive messages Create report Update Car Status Board Controller Send status info Send Ride information | High | 3x6 |
|  | Average | 4 |
| Total |  | 112 |

* + 1. ***External inquiries (EQs)***

An inquiry is a data retrieval request performed by an agent of the system.

PowerEnJoy ensures that the following information can be inquired according to the agent who makes the request, as it is described here:

* A user can retrieve his reservation history.
* An administrator can retrieve the full list of users, safe areas, cars, cars status log, and rides information.
* An operator can retrieve cars status log and users list.

All these operations can be though as fairly simple.

*The resulting table is the following:*

|  |  |  |
| --- | --- | --- |
| EQ | Complexity | FPs |
| Retrieve users reservation history | Low | 3 |
| Retrieve list of users | Low | 3 |
| Retrieve list of safe areas | Low | 3 |
| Retrieve list of cars | Low | 3 |
| Retrieve cars status log | Low | 3 |
| Retrieve rides information | Low | 3 |
| Total |  | 21 |

* + 1. ***External outputs (EOs)***

The main kind of information that PowerEnJoy system must deliver to its agents, in order to provide efficient functionalities, are notifications that must be forwarded to users, administrators, operators and to cars Board Controller:

* Notify the Board Controller that the car has been reserved.
* Notify a user that his request has been accepted.
* Notify a user that his request has been dropped because reservation expired.
* Notify user of payment outcomes.
* Notify operator of new task assignment.
* Notify admin of emergency occurrence.

All these operations can be though as fairly simple.

*The resulting table is the following:*

|  |  |  |
| --- | --- | --- |
| EO | Complexity | FPs |
|  |  |  |
| Board Controller reservation request notification | Low | 4 |
| Request accepted notification | Low | 4 |
| Request dropped notification | Low | 4 |
| Operator task assignment notification | Low | 4 |
| Admin emergency notification | Low | 4 |
| Total |  | 20 |

* + 1. ***Overall estimation***

The following table summarizes the results of our estimation activity:

|  |  |
| --- | --- |
| Function Type | Value |
|  |  |
| Internal Logic Files | 55 |
| External Logic Files | 30 |
| External Inputs | 112 |
| External Inquiries | 21 |
| External Outputs | 20 |
| Total | 238 |

Considering Java Enterprise Edition as a development platform and disregarding the aspects concerning the implementation of the mobile applications (which can be thought as pure presentation with no business logic), we can estimate the total number of lines of code.

Depending on the conversion rate, we have a lower bound of:

SLOC = 238 ∗ 46 = 10948

and an upper bound of

SLOC = 238 ∗ 67 = 15946

* 1. ***Cost and effort estimation COCOMO II***

In this section we're going to use the COCOMO II approach to estimate the cost and effort needed to develop PowerEnjoy.

The effort estimation is achieved through a complex, non linear model that takes into account the characteristics of product and process:

PM = A x SizeE x Π1<=i<=nEMi

* + 1. ***Scale drivers***

The selection of scale drivers is based on the rationale that they are a significant source of exponential variation on a project's effort or productivity variation.

Each scale driver has a range of rating levels, from Very Low to Extra High. Each rating level has a weight, W, and the specific value of the weight is called a scale factor.

In order to evaluate the values of the scale drivers, we refer to the following official COCOMO II table:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *Scale Factors* | *Very Low* | *Low* | *Nominal* | *High* | *Very High* | *Extra High* |
| PREC  SFj | thoroughly  unprecedented  6.20 | largely  unprecedented  4.96 | somewhat unprecedented  3.72 | generally familiar  2.48 | largely familiar  2.48 | thoroughly familiar  0.00 |
| FLEX  SFj | rigorous  5.07 | occasional relaxation  4.05 | some  relaxation  3.04 | general conformity  2.03 | some conformity  1.01 | general goals  0.00 |
| RESL  SFj | little (20%)  7.07 | some (40%)  5.65 | often (60%)  4.24 | generally  (75%)  2.83 | mostly (90%)  1.41 | full (100%)  0.00 |
| TEAM  SFj | very difficult interactions  5.48 | some difficult interactions  4.38 | basically cooperative interactions  3.29 | largely cooperative  2.19 | highly cooperative  1.10 | seamless interactions  0.00 |
| PMAT  SFj | Level 1  Lower  7.80 | Level 1  Upper  6.24 | Level 2  4.68 | Level 3  3.12 | Level 4  1.56 | Level 5  0.00 |

**Precedentedness:** it reflects the previous experience of our team with the development of large scale projects; If a product is similar to several previously developed projects, then the precedentedness is high.

Since we are not expert in the field, this value will be low.

**Development flexibility:** Expresses the degree of conformance to software requirements and external interface standards :as the degree of flexibility in the development process with respect to the external specification and requirements. In this project all the functional requirements are well specified but there are also some free. Consequently the value assigned is nominal.

**Risk resolution:** reflects the level of awareness and reactiveness with

respect to risks. Since we have a good risk management plan, clear definition of budget and schedule, focus on architectural definition we set the very high.

**Team cohesion:** Captures the consistency of stakeholder objectives and the willingness of all parties to work together as a team. For our team, the value is very high.

**Process maturity:** Maturity of the software process used to produce the product; all the goals have been successfully achieved and the software process was followed well, this value is set to level 3.

|  |  |  |
| --- | --- | --- |
| *Scale Driver* | *Factor* | *Value* |
| Precedentedness(PREC)  Development flexibility (FLEX)  Risk resolution (RESL)  Team cohesion (TEAM)  Process maturity (PMAT) | Low  Nominal  Very high  Very high  Level 3 | 4.96  3.04  1.41  1.10  3.12 |
| Total | | 13.63 |

* + 1. ***Cost drivers***

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *RELY Cost Drivers* | | | | | | |
| RUSE  Descriptors | Slightly  inconvenience | Easily recoverable losses | Moderate recoverable losses | High financial loss | Risk to human life |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 0.82 | 0.92 | 1.00 | 1.10 | 1.26 | n/a |

**Required Software Reliability:** Degree of assurance to which the software will performs its intended function:

If the effect of a software failure is only slight inconvenience then RELY is very low.

If a failure would risk human life then RELY is very high.

In PowerEnjoy the rely cost is set to nominal since a software failure not cause large financial loss

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *DATA Cost Drivers* | | | | | | |
| DATA  Descriptors |  | D/P < 10 | 10 ≤ D/P ≥ 100 | 10 ≤ D/P ≥ 1000 | D/P > 1000 |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | n/a | 0.90 | 1.00 | 1.14 | 1.28 | n/a |

**Database size:** this cost driver attempts to capture the effect large test data requirements have on product development.

We don't have the ultimate answer, but our estimation given the tables and \_elds we have is to reach a 3GB database. Since it is distributed over 10.000-15.000 SLOC, the ratio D/P (measured as testing DB bytes/program SLOC) is between 209 and 314, resulting in the DATA cost driver being high

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *CPLX Cost Driver* | | | | | | |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 0.73 | 0.87 | 1.00 | 1.17 | 1.34 | 1.74 |

**Product Complexity:** is set to high since we manage queue and stack control, homogeneous distributed processing and matrix/vector operations.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *RUSE Cost Driver* | | | | | | |
| RUSE  Descriptors |  | None | Across project | Across program | Across product line | Across multiple product lines |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | n/a | 0.95 | 1.00 | 1.07 | 1.15 | 1.24 |

**Required reusability:** accounts for the additional effort needed to construct components intended for reuse on the current or future projects.

In our case, the reusability requirements are limited in scope to the project itself, so the RUSE cost driver is set to nominal.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *DOCU Cost Driver* | | | | | | |
| DOCU  Descriptors | Many  life-cycle  needs  uncovered | Some  life-cycle  needs  uncovered | Right-sized to  life-cycle  needs | Excessive  for life-  cycle  needs | Very-excessive for  life-cycle  needs |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 0.81 | 0.91 | 1.00 | 1.11 | 1.23 | n/a |

**Documentation match to life-cycle needs:** evaluated in terms of the suitability of the project’s documentation to its life-cycle needs. In our case, the DOCU cost driver is set to nominal.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *TIME Cost Driver* | | | | | | |
| TIME  Descriptors |  |  | ≤50% use of available execution time | 70% use of available execution time | 85% use of available execution time | 95% use of available execution time |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | n/a | n/a | 1.00 | 1.11 | 1.29 | 1.63 |

**Execution time constraint:** measure of the execution time constraint imposed upon a software systems, PowerEnjoy uses a lot of cpu for handle the various requests and for manage and keep alive the whole system. We set this parameter high.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *STOR Cost Driver* | | | | | | |
| STOR  Descriptors |  |  | ≤50% use of available execution time | 70% use of available execution time | 85% use of available execution time | 95% use of available execution time |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | n/a | n/a | 1.00 | 1.05 | 1.17 | 1.46 |

**Storage Constraint:** degree of main storage constraint imposed on a software system. As current disk drives can easily contain several terabytes of storage, since we use less than 50%, this value is set to nominal.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *PVOL Cost Driver* | | | | | | |
| PVOL Descriptors |  | Major change every 12 mo., minor change  every 1 mo. | Major: 6mo;  minor: 2wk. | Major:2mo,  minor:1wk | Major: 2wk; mi-nor: 2 days |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | n/a | 0.87 | 1.00 | 1.15 | 1.30 | n/a |

**Platform Volatility:** this rating ranges from low, where there is a major change every 12 months, to very high, where there is a major change every two weeks.

This parameter is set nominal. Indeed only the mobile app requires sporadically updates for the major OS releases.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *ACAP Cost Driver* | | | | | | |
| ACAP Descriptors | 15th percentile | 35th percentile | 55th percentile | 75th percentile | 90th percentile |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 1.42 | 1.19 | 1.00 | 0.85 | 0.71 | n/a |

**Analyst Capability:** the major attributes that should be considered in this rating are Analysis and Design ability, efficiency and thoroughness, and the ability to communicate and cooperate.

The rating should not consider the level of experience of the analyst;

that is rated with AEXP.

Analysts that fall in the 15th percentile are rated very low and those that fall in the 95th percentile are rated as very high.

based on this index, and with respect to how the our analysis was conducted we assign the value high.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *CAP Cost Driver* | | | | | | |
| PCAP Descriptors | 15th percentile | 35th percentile | 55th percentile | 75th percentile | 90th percentile |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 1.34 | 1.15 | 1.00 | 0.88 | 0.76 | n/a |

**Programmer Capability:** since in this index we evaluate the capability of the programmers as a team rather than as individuals we set this index to high.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *APEX Cost Driver* | | | | | | |
| APEX Descriptors | ≤ 2 months | 6 months | 1 year | 3 year | 6 year |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 1.22 | 1.10 | 1.00 | 0.88 | 0.81 | n/a |

**Applications Experience:** dependent on the level of applications experience of the project team developing the software system or subsystem; We have some experience in the development of Java applications, but we never tackled a Java EE system of this kind. For this

reason we're going to set this parameter to low.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *PLEX Cost Driver* | | | | | | |
| PLEX Descriptors | ≤ 2 months | 6 months | 1 year | 3 year | 6 year |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 1.19 | 1.09 | 1.00 | 0.91 | 0.85 | n/a |

**Platform Experience:** the rating for this cost driver (formerly labeled AEXP) is dependent on the level of applications experience of the project team developing the software system or subsystem.

We have some previous experience with databases, user interfaces and server side development. For this reason, we're going to set this parameter to nominal.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *LTEX Cost Driver* | | | | | | |
| LTEX Descriptors | ≤ 2 months | 6 months | 1 year | 3 year | 6 year |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 1.20 | 1.09 | 1.00 | 0.91 | 0.84 | n/a |

**Language and Tool Experience:** we don't have any experience with the Java EE platform and with the development of mobile application but we have some previous experience with databases, user interfaces and server side development. We are also knowledgable of the development environment, so we're going to set this parameter to nominal.

Project factors account for influences on the estimated effort such as use of modern software tools, location of the development team, and compression of the project schedule.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *PCON Cost Driver* | | | | | | |
| PCON Descriptors | 48% / year | 24% / year | 12% / year | 6% / year | 3% / year |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 1.29 | 1.12 | 1.00 | 0.90 | 0.81 | n/a |

**Personnel continuity:** the rating scale for PCON is in terms of the project’s annual personnel turnover: This parameter is set to very high since in our case the act of replacing an employee with a new employee is rare.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *TOOL Cost Driver* | | | | | | |
| TOOL Descriptors | edit, code,  debug | simple,  frontend,  backend  CASE,  little integration | basic  life-cycle  tools,  moderately  integrated | strong,  mature  life-cycle  tools,  moderately  integrated | strong,  mature,  proactive  life-cycle tools, well  integrated  with processes,  methods,  reuse |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 1.17 | 1.09 | 1.00 | 0.90 | 0.78 | n/a |

**Usage of Software Tools:** the tool rating ranges from simple edit and code, very low, to integrated life-cycle management tools, very high.

Our application environment is complete and well integrated, so we'll set this parameter as high.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *SITE Cost Driver* | | | | | | |
| SITE  Collocation Descriptors  SITE Communications  Descriptors | Intern-  Ational  Some  phone,  mail | Multi-city  and multi-  company  Individual  phone, fax | Multi-city  or multi-  company  Narrow  band  email | Same city  or metro  area  Wideband  electronic  communi-  cation | Same building or complex Wideband elect. Comm., occasional video conf. | Fully collocated  Interactive multimedia |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 1.22 | 1.09 | 1.00 | 0.93 | 0.86 | 0.80 |

**Multisite development:** the team’s components lives in different cities and collaborates using different wideband internet services, including e-mail and video conferences.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *SCED Cost Driver* | | | | | | |
| SCED  Collocation Descriptors | 75% of  nominal | 85% of  nominal | 100% of  nominal | 130% of  nominal | 160% of  nominal |  |
| Rating level | Very low | Low | Nominal | High | Very high | Extra high |
| Effort multipliers | 1.43 | 1.14 | 1.00 | 1.00 | 1.00 | n/a |

**Required development schedule:**

This rating measures the schedule constraint imposed on the project team developing the software. The ratings are defined in terms of the percentage of schedule stretch-out or acceleration with respect to a nominal schedule for a project requiring a given amount of effort.

Even if the entire work was well distributed over the available development time, the definition of all the required documentation took a consistent amount of time, especially for the requirement analysis and the design phases. For this reason, this parameter is set to high.

|  |  |  |
| --- | --- | --- |
| *Cost Driver* | *Factor* | *Value* |
| Required Software Reliability (RELY)  Database size (DATA)  Product complexity (CPLX)  Required Reusability (RUSE)  Documentation match to life-cycle needs(DOCU)  Execution Time Constraint (TIME)  Main storage constraint (STOR)  Platform volatility (PVOL)  Analyst capability (ACAP)  Programmer capability (PCAP)  Application Experience (APEX)  Platform Experience (PLEX)  Language and Tool Experience (LTEX)  Personnel continuity (PCON)  Usage of Software Tools (TOOL)  Multisite development (SITE)  Required development schedule (SCED) |  |  |
| Total |  |  |

1. ***Schedule***
2. ***Resource allocation***
3. ***Risk management***

During the analysis phase of the project, a few risks have been identified as potential dangers for the project.

First, due to the need for urban permissions to build power charge stations and the high cost needed for their construction, overall costs could raise rapidly, especially if PowerEnJoy wants the power stations to be fairly distributed.

Second, due to the unpredictable nature of the customers, it might happen to be in need to go take back in the city a car that was brought of the prefixed boundaries. This could cause an increase in costs and might also have legal consequences.

Third, battery degradation over time is definitely a factor that must be taken into account. Due to the volatile nature of the good, battery replacements may result in a substantial cost voice.

A solution to these three kinds of risk is not immediately identifiable. The suggestion is to take into account the need for an extra budget, exceeding the one allocated for common manutention operations, to be used in case such emergencies should occur.

Finally, time constraints might be not respected due to any problem in the development chain. This could eventually cause delays in the implementation of the project.

To manage this last eventuality, the estimation for the hours needed to conclude the project have been overestimated by a 30%.

1. ***Revision***
   * 1. ***Team work***

Here is reported a compact table showing how the work was brought on by all the members of the group.

Document work finished on the xth January 2017.

